## ADaM tracker
Dataset | Class | SDTM source | Implementation script | Spec reference | Downstream analyses | Output file | Records | Size (KB) | Primary programmer | Programmed date | QC programmer | QC method | QC start date | QC complete date | Status | Findings / issues | Resolution | Lock date | Comments
ADAE | Occurrence Data Structure | AE + ADSL | programs/adam/adae.R | ADAM-MAPPING-SPEC.md §2 | T-AE-01..07, L-AE-01/03 | datasets/adam/adae.parquet | 2,841 | 109.7 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADCM | Occurrence Data Structure | CM + SUPPCM + ADSL | programs/adam/adcm.R | ADAM-MAPPING-SPEC.md §10 | T-CM-01 | datasets/adam/adcm.parquet | 2,330 | 71.4 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADDS | Occurrence Data Structure | DS + ADSL | programs/adam/adds.R | ADAM-MAPPING-SPEC.md §7 | T-DS-01 | datasets/adam/adds.parquet | 1,350 | 35.4 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADDV | Occurrence Data Structure | DV + ADSL | programs/adam/addv.R | ADAM-MAPPING-SPEC.md §8 | T-DS-02, T-DV-01, L-DS-01 | datasets/adam/addv.parquet | 337 | 25.1 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADEX | Basic Data Structure | EX + ADSL | programs/adam/adex.R | ADAM-MAPPING-SPEC.md §9 | T-EX-01 (DOSEAMT/CUMDOSE/RDI) | datasets/adam/adex.parquet | 16,097 | 116.5 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADLB | Basic Data Structure | LB + ADSL | programs/adam/adlb.R | ADAM-MAPPING-SPEC.md §3 | T-LB-01/02, L-LB-01 | datasets/adam/adlb.parquet | 122,601 | 1487.8 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADMH | Occurrence Data Structure | MH + ADSL | programs/adam/admh.R | ADAM-MAPPING-SPEC.md §12 | T-MH-01 | datasets/adam/admh.parquet | 2,061 | 41.6 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADRS | Basic Data Structure | RS + ADSL + ADTR | programs/adam/adrs.R | ADAM-MAPPING-SPEC.md §5 | T-EFF-05 (ORR), T-EFF-06 (DCR), T-EFF-13 (ORR-ITT) | datasets/adam/adrs.parquet | 3,662 | 39.9 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADSL | Subject-Level Analysis Dataset | DM + SUPPDM + EX + DS + DD | programs/adam/adsl.R | ADAM-MAPPING-SPEC.md §1 | All — anchor | datasets/adam/adsl.parquet | 450 | 37 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADTR | Basic Data Structure | TR + ADSL | programs/adam/adtr.R | ADAM-MAPPING-SPEC.md §4 | F-EFF-03 (Waterfall), F-EFF-04 (Spider) | datasets/adam/adtr.parquet | 9,378 | 165.5 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADTTE | Basic Data Structure | ADSL + ADRS + DS + DD | programs/adam/adtte.R | ADAM-MAPPING-SPEC.md §6 | T-EFF-01..04, T-EFF-07..12, F-EFF-01/02/05/06 | datasets/adam/adtte.parquet | 2,368 | 32.6 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC
ADVS | Basic Data Structure | VS + ADSL | programs/adam/advs.R | ADAM-MAPPING-SPEC.md §11 | T-VS-01, T-VS-02 | datasets/adam/advs.parquet | 52,864 | 516.8 |  | 2026-05-17 |  | Independent double programming |  |  | Programmed — pending QC

## Status legend
Status | Meaning
Not started | Output has not been programmed yet. No code, no parquet, no TFL file.
Programmed — pending QC | Primary programmer has produced the output. Awaiting assignment to a QC programmer.
QC in progress | Independent QC programmer is actively re-programming and comparing.
QC passed — issues none | QC double-programming passed. Outputs match within tolerance. No issues raised.
QC passed — minor issues resolved | QC found minor issues (typos, formatting) — resolved before sign-off.
QC failed — under rework | QC found substantive differences. Output is being reworked by primary programmer.
Locked | Output approved and locked for the snapshot. Any change triggers re-QC.

## Sign-off
ADaM Programming — Sign-off sheet
Generated 2026-05-17 — synthetic data, not for regulatory submission
Role | Name | Signature | Date | Comment
Lead programmer
Lead QC programmer
Biostatistician (analysis review)
Data manager
Project manager
Quality assurance
Sponsor representative