## SDTM tracker
Domain | Class | Source (raw / SDTM) | Implementation script | Spec reference | Output file | Records | Size (KB) | Primary programmer | Programmed date | QC programmer | QC method | QC start date | QC complete date | Status | Findings / issues | Resolution | Lock date | Comments
AE | Events | raw/adverse_events.csv + meddra_oncology_subset.csv | programs/sdtm/ae.R | SDTM-MAPPING-SPEC.md §5 | datasets/sdtm/ae.parquet | 2,841 | 60.1 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
CM | Interventions | raw/conmed.csv + atc_conmed.csv | programs/sdtm/cm.R | SDTM-MAPPING-SPEC.md §6 | datasets/sdtm/cm.parquet | 2,197 | 31.7 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC | AL-02: cm.parquet does not include post-trial anti-cancer therapy (only supportive-care meds). Affects T-DS-03 + T-EFF-12. Accepted — not a defect.
DA | Interventions | raw/drug_accountability.csv | programs/sdtm/da.R | SDTM-MAPPING-SPEC.md §4 | datasets/sdtm/da.parquet | 31,866 | 123.8 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
DD | Events | raw/death.csv | programs/sdtm/dd.R | SDTM-MAPPING-SPEC.md §9 | datasets/sdtm/dd.parquet | 312 | 12.9 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
DM | Special purpose | raw/demographics.csv | programs/sdtm/dm.R | SDTM-MAPPING-SPEC.md §1 | datasets/sdtm/dm.parquet | 450 | 24.1 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
DS | Events | raw/demographics.csv + raw/disposition.csv | programs/sdtm/ds.R | SDTM-MAPPING-SPEC.md §2 | datasets/sdtm/ds.parquet | 1,350 | 16.6 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC | AL-03: SDTM.DS does not carry explicit DSCAT='PROTOCOL DEVIATION' records; only PPROTFL='N' is derivable. Accepted — not a defect.
EX | Interventions | raw/exposure.csv | programs/sdtm/ex.R | SDTM-MAPPING-SPEC.md §3 | datasets/sdtm/ex.parquet | 13,403 | 80.7 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
LB | Findings | raw/labs.csv | programs/sdtm/lb.R | SDTM-MAPPING-SPEC.md §10 | datasets/sdtm/lb.parquet | 122,601 | 706.1 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
MH | Events | raw/medical_history.csv | programs/sdtm/mh.R | SDTM-MAPPING-SPEC.md §7 | datasets/sdtm/mh.parquet | 2,061 | 25.7 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
PE | Findings | raw/physical_exam.csv | programs/sdtm/pe.R | SDTM-MAPPING-SPEC.md §12 | datasets/sdtm/pe.parquet | 25,596 | 67.2 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
RELREC | Relationship | tu.parquet + tr.parquet + rs.parquet | programs/sdtm/relrec.R | SDTM-MAPPING-SPEC.md §21 | datasets/sdtm/relrec.parquet | 21,162 | 60.2 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC | AL-11: relrec.parquet contains duplicate rows (~5 per multi-visit lesion) because relrec.R emits one row per TU/TR record rather than one per unique lesion-id. compare_sdtm.R falls back to identical() comparison. Future relrec.R revision should distinct() on (USUBJID, RDOMAIN, IDVARVAL). Accepted — not a defect.
RS | Findings | raw/overall_response.csv | programs/sdtm/rs.R | SDTM-MAPPING-SPEC.md §15 | datasets/sdtm/rs.parquet | 2,762 | 25.7 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
SU | Interventions | raw/substance_use.csv | programs/sdtm/su.R | SDTM-MAPPING-SPEC.md §8 | datasets/sdtm/su.parquet | 1,217 | 14.7 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
SUPPAE | Relationship | ae.parquet + raw/adverse_events.csv | programs/sdtm/suppae.R | SDTM-MAPPING-SPEC.md §18 | datasets/sdtm/suppae.parquet | 8,523 | 13.6 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
SUPPCM | Relationship | cm.parquet | programs/sdtm/suppcm.R | SDTM-MAPPING-SPEC.md §19 | datasets/sdtm/suppcm.parquet | 4,394 | 14.8 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
SUPPDM | Relationship | raw/demographics.csv | programs/sdtm/suppdm.R | SDTM-MAPPING-SPEC.md §16 | datasets/sdtm/suppdm.parquet | 1,799 | 15.1 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
SUPPLB | Relationship | lb.parquet | programs/sdtm/supplb.R | SDTM-MAPPING-SPEC.md §20 | datasets/sdtm/supplb.parquet | 245,202 | 108.3 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
SUPPSU | Relationship | raw/substance_use.csv (legacy) | (generator missing — see spec §17) | SDTM-MAPPING-SPEC.md §17 | datasets/sdtm/suppsu.parquet | 450 | 9.8 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC | AL-01: SUPPSU is a legacy artifact (STUDYID 'TORIVUMAB-NSCLC-301', not 'CTX-NSCLC-301'); no generator script in programs/sdtm/. See SDTM-MAPPING-SPEC.md §17. Accepted — not a defect.
TR | Findings | raw/tumor_measurements.csv | programs/sdtm/tr.R | SDTM-MAPPING-SPEC.md §14 | datasets/sdtm/tr.parquet | 9,200 | 80.3 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
TU | Findings | raw/tumor_measurements.csv | programs/sdtm/tu.R | SDTM-MAPPING-SPEC.md §13 | datasets/sdtm/tu.parquet | 9,148 | 46 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC
VS | Findings | raw/vital_signs.csv | programs/sdtm/vs.R | SDTM-MAPPING-SPEC.md §11 | datasets/sdtm/vs.parquet | 52,864 | 307.2 |  | 2026-05-16 |  | Independent double programming |  |  | Programmed — pending QC

## Status legend
Status | Meaning
Not started | Output has not been programmed yet. No code, no parquet, no TFL file.
Programmed — pending QC | Primary programmer has produced the output. Awaiting assignment to a QC programmer.
QC in progress | Independent QC programmer is actively re-programming and comparing.
QC passed — issues none | QC double-programming passed. Outputs match within tolerance. No issues raised.
QC passed — minor issues resolved | QC found minor issues (typos, formatting) — resolved before sign-off.
QC failed — under rework | QC found substantive differences. Output is being reworked by primary programmer.
Locked | Output approved and locked for the snapshot. Any change triggers re-QC.

## Sign-off
SDTM Programming — Sign-off sheet
Generated 2026-05-16 — synthetic data, not for regulatory submission
Role | Name | Signature | Date | Comment
Lead programmer
Lead QC programmer
Biostatistician (analysis review)
Data manager
Project manager
Quality assurance
Sponsor representative