## TFL tracker
Output ID | Kind | Title | Analysis set | Source dataset(s) | Shell reference | Implementation script | Output files | SAP reference | Estimand ID | Primary programmer | Programmed date | QC programmer | QC method | QC start date | QC complete date | Status | Findings / issues | Resolution | Lock date | Comments
T-DM-01 | table | Demographic and Baseline Characteristics | ITT | ADSL | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_dm_01*.R | tfl/tables/T-DM-01.{rtf, docx, html} | §3.1 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-DS-01 | table | Subject Disposition | ITT | ADSL | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ds_01*.R | tfl/tables/T-DS-01.{rtf, docx, html} | §3 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-DS-02 | table | Major Protocol Deviations | ITT | ADSL, SDTM.DS | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ds_02*.R | tfl/tables/T-DS-02.{rtf, docx, html} | §3.2 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-DS-03 | table | Intercurrent Events Summary | ITT | ADSL, ADAE, ADTTE, SDTM.CM | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ds_03*.R | tfl/tables/T-DS-03.{rtf, docx, html} | §13.3 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC | AL-10: Subsequent anti-cancer therapy row shows 0 (synthetic CM does not simulate post-trial therapy). Missed-assessments row populated from SDTM.DV as of 2026-05-17. Accepted — not a defect.
T-EX-01 | table | Study Drug Exposure | SAFETY | ADSL | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ex_01*.R | tfl/tables/T-EX-01.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-01 | table | Overall Survival Analysis (Primary) | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_01*.R | tfl/tables/T-EFF-01.{rtf, docx, html} | §5.1 | E1 |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-02 | table | Kaplan-Meier Survival Probabilities — OS | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_02*.R | tfl/tables/T-EFF-02.{rtf, docx, html} | §5.1 | E1 |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-03 | table | Progression-Free Survival Analysis (BICR) | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_03*.R | tfl/tables/T-EFF-03.{rtf, docx, html} | §5.2 | E2 |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-04 | table | Kaplan-Meier Probabilities — PFS | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_04*.R | tfl/tables/T-EFF-04.{rtf, docx, html} | §5.2 | E2 |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-05 | table | Objective Response Rate (BICR) | RESPEVAL | ADRS, ADSL | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_05*.R | tfl/tables/T-EFF-05.{rtf, docx, html} | §5.3 | E3 |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-06 | table | Disease Control Rate | RESPEVAL | ADRS, ADSL | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_06*.R | tfl/tables/T-EFF-06.{rtf, docx, html} | §5.3 | E5 |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-07 | table | Duration of Response | RESPONDERS | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_07*.R | tfl/tables/T-EFF-07.{rtf, docx, html} | §5.4 | E4 |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-08 | table | OS in Per-Protocol Population (Sensitivity) | PP | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_08*.R | tfl/tables/T-EFF-08.{rtf, docx, html} | §11 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-09 | table | OS Landmark Analysis | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_09*.R | tfl/tables/T-EFF-09.{rtf, docx, html} | §11 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-EFF-10 | table | Restricted Mean Survival Time (OS) | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_10*.R | tfl/tables/T-EFF-10.{rtf, docx, html} | §11 | E1a |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC | AL-06: τ = 30 months (not the SAP-proposed 36 months) bounded by max follow-up. See footnote in t_eff_10_os_rmst.R. Accepted — not a defect.
T-EFF-11 | table | PFS by Investigator (Sensitivity) | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_11*.R | tfl/tables/T-EFF-11.{rtf, docx, html} | §4.2 | E2a |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC | AL-07: PFS-INV ≡ PFS in synthetic data (no separate BICR). Identical results to T-EFF-03 expected. Accepted — not a defect.
T-EFF-12 | table | Overall Survival — While-on-Treatment Sensitivity | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_12*.R | tfl/tables/T-EFF-12.{rtf, docx, html} | §13.4 | E1b |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC | AL-02 + AL-10: subsequent anti-cancer therapy not simulated; OSWOT censoring applies only the TRTEDT + 30d component. Accepted — not a defect.
T-EFF-13 | table | Objective Response Rate — ITT Denominator (Sensitivity) | ITT | ADSL, ADRS | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_eff_13*.R | tfl/tables/T-EFF-13.{rtf, docx, html} | §13.6 | E3a |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-AE-01 | table | Overall Summary of AEs | SAFETY | ADSL, ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ae_01*.R | tfl/tables/T-AE-01.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-AE-02 | table | TEAEs by SOC and PT (≥5% any arm) | SAFETY | ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ae_02*.R | tfl/tables/T-AE-02.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-AE-03 | table | Grade ≥3 TEAEs by SOC and PT | SAFETY | ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ae_03*.R | tfl/tables/T-AE-03.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-AE-04 | table | Serious Adverse Events by SOC and PT | SAFETY | ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ae_04*.R | tfl/tables/T-AE-04.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-AE-05 | table | Immune-Related AEs by Category | SAFETY | ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ae_05*.R | tfl/tables/T-AE-05.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-AE-06 | table | AESIs by Category | SAFETY | ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ae_06*.R | tfl/tables/T-AE-06.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC | AL-08: AESI categorisation uses MedDRA-PT regex stand-in pending SAP §4.6 deferred AESI list. Accepted — not a defect.
T-AE-07 | table | Deaths | SAFETY | ADSL, ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_ae_07*.R | tfl/tables/T-AE-07.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-LB-01 | table | Laboratory Abnormalities (Shift Table) | SAFETY | ADLB | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_lb_01*.R | tfl/tables/T-LB-01.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-LB-02 | table | Laboratory CTCAE Grade ≥3 | SAFETY | ADLB | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_lb_02*.R | tfl/tables/T-LB-02.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
F-EFF-01 | figure | Kaplan-Meier Curve — OS | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/f_eff_01*.R | tfl/figures/F-EFF-01.png | §5.1 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
F-EFF-02 | figure | Kaplan-Meier Curve — PFS | ITT | ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/f_eff_02*.R | tfl/figures/F-EFF-02.png | §5.2 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
F-EFF-03 | figure | Waterfall — Best Percent Change in SLD | RESPEVAL | ADTR | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/f_eff_03*.R | tfl/figures/F-EFF-03.png | §5.3 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
F-EFF-04 | figure | Spider — SLD Change Over Time | RESPEVAL | ADTR | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/f_eff_04*.R | tfl/figures/F-EFF-04.png | §5.3 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
F-EFF-05 | figure | Forest — OS HR by Subgroup | ITT | ADSL, ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/f_eff_05*.R | tfl/figures/F-EFF-05.png | §10 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
F-EFF-06 | figure | Swimmer — Responders | RESPONDERS | ADSL, ADRS, ADTTE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/f_eff_06*.R | tfl/figures/F-EFF-06.png | §5.4 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
L-AE-01 | listing | Serious Adverse Events | SAFETY | ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/l_ae_01*.R | tfl/tables/L-AE-01.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
L-AE-02 | listing | Deaths | SAFETY | ADSL | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/l_ae_02*.R | tfl/tables/L-AE-02.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
L-AE-03 | listing | AEs Leading to Discontinuation | SAFETY | ADAE | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/l_ae_03*.R | tfl/tables/L-AE-03.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
L-LB-01 | listing | Grade ≥3 Laboratory Abnormalities | SAFETY | ADLB | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/l_lb_01*.R | tfl/tables/L-LB-01.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
L-DS-01 | listing | Major Protocol Deviations | ITT | SDTM.DS | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/l_ds_01*.R | tfl/tables/L-DS-01.{rtf, docx, html} | §3.2 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-CM-01 | table | Concomitant Medications by Class and Preferred Term | SAFETY | ADCM | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_cm_01*.R | tfl/tables/T-CM-01.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-VS-01 | table | Vital Signs — Mean Change from Baseline at Key Visits | SAFETY | ADVS | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_vs_01*.R | tfl/tables/T-VS-01.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-VS-02 | table | Weight Change Categories — Worst On-Treatment % Change | SAFETY | ADVS | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_vs_02*.R | tfl/tables/T-VS-02.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-MH-01 | table | Medical History by Category and Term | SAFETY | ADMH | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_mh_01*.R | tfl/tables/T-MH-01.{rtf, docx, html} | §5.5 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC
T-DV-01 | table | Protocol Deviations — Detail | ITT | ADDV | shells.yaml + TFL-SHELLS-DOC.docx | programs/tfl/t_dv_01*.R | tfl/tables/T-DV-01.{rtf, docx, html} | §3.2 |  |  | 2026-05-17 |  | Independent double programming + footer reconciliation |  |  | Programmed — pending QC

## Status legend
Status | Meaning
Not started | Output has not been programmed yet. No code, no parquet, no TFL file.
Programmed — pending QC | Primary programmer has produced the output. Awaiting assignment to a QC programmer.
QC in progress | Independent QC programmer is actively re-programming and comparing.
QC passed — issues none | QC double-programming passed. Outputs match within tolerance. No issues raised.
QC passed — minor issues resolved | QC found minor issues (typos, formatting) — resolved before sign-off.
QC failed — under rework | QC found substantive differences. Output is being reworked by primary programmer.
Locked | Output approved and locked for the snapshot. Any change triggers re-QC.

## Sign-off
TFL Programming — Sign-off sheet
Generated 2026-05-17 — synthetic data, not for regulatory submission
Role | Name | Signature | Date | Comment
Lead programmer
Lead QC programmer
Biostatistician (analysis review)
Data manager
Project manager
Quality assurance
Sponsor representative